## Sheet1
Task Name | Estimation | 2012-07-13 | 2012-07-18 | 2012-08-05
create KinokoTask class with delegate and category. | 3 |  | 2
implement provider that loads all the valid methods from a list of assemblies. | 4
implement provider that loads all the marked methods from a list of assemblies. | 4
implement provider that loads the specified methods from a list of assemblies. | 4
parse console attributes. | 4 |  |  | 6
create the help and display in the console. | 4 |  |  | 1
refactoring the console - create unit tests | 8
Total | 31 | 0 | 2 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remained | 31 | 31 | 29 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22